## Weekly Plan
12/11 - 16/11 | Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday
| Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
8:30 |  |  | Weekly Plan | Weekly Plan | Catch up with current events/news | Catch up with current events/news | Catch up with current events/news |  | Catch up with current events/news
9:00 |  |  |  |  | git pull | PC setup (PC was bugging up and wifi was not working) | git pull in branch |  | git pull
9:30 |  |  |  |  | Research Database integration with Java EE [Req-04] |  | Req-04 |  | Implement Req-05
10:00 |  |  | Research Jenkins, Design Patterns | Breakfast / Research Jenkins
10:30
11:00 |  |  | Setup GitLab/GitHub | Setup GitHub | Design and Setup Database tables | Setting up work environment and Jenkins
11:30 |  |  | Training Modules | [5 empty] | Code Review
12:00 |  |  |  | Training Modules |  | Documentation for Jenkins created and saved to local machine
12:30 |  |  | Lunch |  | Lunch | Implement Req-01 class Account, AccountFactory, UserFactory, and related test classes | Lunch |  | Lunch
13:00 |  |  |  | Lunch
13:30 |  |  | Implement Req-01 |  | Implement Req-02 | Lunch | Design and Create Database and tables |  | Implement Req-06
14:00 |  |  |  | Implement Req-01
14:30 |  |  |  |  | Implement Req-03, git push | Implement Req-01, git push
15:00 | [5 empty] | Implement Req-02
15:30 | [6 empty] | Implement Persistence, git merge branch
16:00 | [5 empty] | Started Implementing Req-03
16:30 |  |  | Training Modules | Set up Jenkins
17:00 |  |  | EOD Activities |  | EOD Activities | EOD Activities | EOD Activities |  | EOD Activities
Deliverables |  |  | Project set up, class User and functions | Class User + functions, Git Project | Req-02, Req-03 | Set up Jenkins, Tomcat, Documentation for Jenkins installation, Req-01, Req-02 | DAO/Persistence, Database Implemented |  | Uploading/Downloading functionality for Portfolios
19/11 - 23/11 | Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday
| Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
8:30 | Catch up with current events/news |  | Catch up with current events/news |  | Catch up with current events/news |  | Catch up with current events/news |  | Catch up with current events/news
9:00 | git pull |  | Implement Req-07 |  | git pull |  | Research In-browser tools to run applications, APIs
9:30 | Work on front-end designs for Project |  |  |  | Design and Implement Req-09
10:00
10:30
11:00
11:30
12:00
12:30 | Lunch |  | Lunch |  | Lunch |  | Lunch |  | Lunch
13:00
13:30 | Work on front-end designs for Project |  | Implement Req-08 |  | Implement Req-10 |  | Integrate in-browser tool with system |  | Leave
14:00
14:30
15:00
15:30
16:00
16:30 | Training Modules |  |  |  | Training Modules |  | Training Modules
17:00 | EOD Activities |  | EOD Activities |  | EOD Activities |  | EOD Activities
Deliverables | Front End for system |  | User Portfolio/Account access management |  | User Portfolio/Account access management |  | Initial Prototype ready for demo

## Backlog
Task ID | Task Description / Requirement | Date Started | Date Completed | Time Expected (hrs) | Time Taken (hrs) | Time Spent (hrs) | Administrative tasks | Repeated on
0 | Revise on Java material learnt during training | 2018-11-01 |  | 60 |  | 30
1 | I want to be able to login to my account profile | 2018-11-13 |  | 3 |  |  | All development must be stored pushed to GitLab SVM | Friday 12pm
2 | Each account will have a portfolio |  |  | 1 |  |  | Update Billy/Aleks/Joe of current progress | Wednesday 2pm
3 | Only registered users can access a portfolio |  |  | 1 |  |  | Interview Prep
4 | Research on which DB is feasible |  |  | 3
5 | I want to store files in a web server |  |  | 8
6 | A registered user can upload files to their portfolios |  |  | 8
7 | A registered user can view files in their portfolios |  |  | 3
8 | A registered user can view files in other users' portfolios |  |  | 1
9 | A registered user can download files from any visible portfolio |  |  | 3
10 | The visibility/publicness of a protfolio can be modified (public, protected, private) |  |  | 3
11 | Research on in-browser app running tools |  |  | 6
12 | I want to be able to run applications in-browser. |  |  | 6
Total |  |  |  | 46